Quarterly Report – Public Page

Date of Report: 13th Quarterly Report – December 31, 2024

Contract Number: #693JK32110008POTA

Prepared for: DOT and Co-funders

Project Title: Advancement of Through-tubing Casing Inspection for Underground Storage Wells

Prepared by: Pipeline Research Council International, Inc.

Contact Information: Carolyn DesCoteaux (CDescoteaux@prci.org)

For quarterly period ending: December 31, 2024

1: Items Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |
| 35 | 5 | 13th quarterly status report & project management | Submit 13th quarterly report | $0 | $0 |

2: Items Not Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |
| 20 | 4 | Conduct Field Trial | Results to be included in the quarterly report | $133,990.40 | $133,990.40 |
| 22 | 3 | Final framework for reliability-based casing integrity management | Results to be included in the quarterly report | $31,206.40 | $31,206.40 |
| 26 | 5 | Submit draft final report | Submit draft final report | $21,490.83 | $23,652.60 |

3: Project Financial Tracking During this Quarterly Period:

The contractor did not supply a financial tracking table.

4:  Project Technical Status:

A no-cost time extension has been submitted, with a proposed end date of September 30, 2025.

[Item #27] [Task #5] [13th quarterly status report & project management] [Submit 13th quarterly report]

The update meeting scheduled for December 2024 was canceled because there were no new updates, as the field trial is still ongoing.

5: Project Schedule:

Anticipated schedule of delayed tasks:

[Item #20] [Task #4] [Conduct field trial] [Results to be included in the quarterly report]

The field trial has commenced in November, 2024. GOWell has logged the test well on November 14th, 2024. The test for Baker Hughes is yet awaiting to be scheduled.

[Item #22] [Task #3] [Final framework for reliability-based casing integrity management] [Results to be included in the quarterly report]

The final framework for reliability-based casing integrity management is anticipated to be completed in Q14.

[Item #26] [Task #5] [Submit draft final report [Submit draft final report]

The draft final report is pending the completion of the field trial.