Quarterly Report – Public Page

Date of Report: 7th Quarterly Report – June 30, 2025

Contract Number: # 693JK32310004POTA

Prepared for: DOT and Co-funders

Project Title: Implement Fiber Optic Technology for Underground Gas Storage Well Monitoring

Prepared by: Pipeline Research Council International, Inc.

Contact Information: Carolyn DesCoteaux (CDescoteaux@prci.org)

For quarterly period ending: June 30, 2025

1: Items Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |
| 7 | 2 | Setup and commission DSS laboratory test apparatus | Test setup description to be included in the quarterly report | $80,600.00 | $80,600.00 |
| 8 | 2 | Conduct DSS laboratory tests | Test execution summary to be included in the quarterly report | $23,175.00 | $23,175.00 |
| 10 | 2 | Setup and commission DAS laboratory test apparatus | Test setup description to be included in the quarterly report | $42,385.00 | $42,385.00 |
| 11 | 2 | Conduct DAS laboratory tests | Test execution summary to be included in the quarterly report | $31,226.00 | $31,226.00 |
| 16 | 4 | 7th quarterly status report & project management | Submit 7th quarterly report | $4,805.00 | $4,805.00 |

2: Items Not Completed During this Quarterly Period:

| Item # | Task # | Activity/Deliverable | Title | Federal Cost | Cost Share |
| --- | --- | --- | --- | --- | --- |
| 13 | 2 | DAS and DSS test performance evaluation | Results to be included in the quarterly report | $36,806.00 | $36,806.00 |
| 15 | 3 | Development of guidelines and best practices | Summary to be included in the quarterly report | $34,441.00 | $34,441.00 |

3: Project Financial Tracking During this Quarterly Period:

4:  Project Technical Status:

[Item #7] [Task #2] [Setup and commission DSS laboratory test apparatus] [Test setup description to be included in the quarterly report]

The DSS test setup and commission were successfully completed in April 2025. Details of the DSS test setup and commission is summarized in Appendix A of this quarterly report.

[Item #8] [Task #2] [Conduct DSS laboratory tests] [Test execution summary to be included in the quarterly report]

The DSS test was successfully conducted on April 30th and May 1st, 2025. Details of the DSS test execution is summarized in Appendix A of this quarterly report.

[Item #10] [Task #2] [Setup and commission DAS laboratory test apparatus] [Test setup description to be included in the quarterly report]

The DAS test setup and commission were successfully completed in May 2025. Details of the DAS test setup and commission is summarized in Appendix A of this quarterly report.

[Item #11] [Task #2] [Conduct DAS laboratory tests] [Test execution summary to be included in the quarterly report]

The DAS test was successfully conducted on May 7th and 12th, 2025. Details of the DAS test execution is summarized in Appendix A of this quarterly report.

[Item #16] [Task #4] [7th quarterly status report & project management] [Submit 7th quarterly report]

A quarterly Technical Advisory Panel (TAP) meeting was held on June 11th, 2025. An update of the DSS & DAS laboratory test was presented, including an overview of the test execution and the preliminary evaluation of the vendor DSS systems. This task is completed.

5: Project Schedule:

[Item #13] [Task #2] [DAS and DSS test performance evaluation] [Results to be included in the quarterly report]

This task is currently ongoing and will be completed in the next quarter.

[Item #15] [Task #3] [Development of guidelines and best practices] [Summary to be included in the quarterly report]

This task is currently ongoing and will be completed in the next quarter.